EXECUTION PLAN

Aura Living

Premium Home Decor E-Commerce Frontend

Phased Build Checklist

Derived from the Frontend Architecture Plan v1.1

Stack: Next.js 16 · TypeScript · Tailwind 4 · GSAP · Framer Motion · Lenis

Market: Pakistan   ·   Timeline: 9 weeks, 5 phases   ·   June 2026

# How to use this document

This is the working build checklist for Aura Living. It turns the five-phase roadmap from Chapter 14 of the architecture plan into discrete, tickable tasks, and folds in the fourteen v1.1 review chapters (testing, security, i18n, PWA, gift options, server-state, promotions, tokens, state catalogs, privacy, search, SEO edge cases, engineering workflow, and miscellany) at the phase where each one actually gets built.

Tick each ☐ as it is completed. Do not advance to the next phase until that phase's Exit Criterion (the gold-bordered box) is fully met — the architecture plan is explicit that rushing a phase compounds problems downstream. The Phase 0 pre-flight is the single most important set of checks: it resolves the open bundle-budget question before any code is written.

Each task notes the relevant plan chapter in brackets so you can trace it back to the full specification.

## Phase summary

| Phase | Weeks | Focus | Gate |
| --- | --- | --- | --- |
| 0 | — | Pre-flight: budget reconciliation, decisions locked | Budgets hold |
| 1 | 1–2 | Foundation: stack, tokens, folders, CI/CD, staging | Staging live, CI green |
| 2 | 3–5 | Core pages: home, PLP, PDP, cart, checkout, confirm | Journey works, LH 70+ |
| 3 | 6–7 | Polish: GSAP, Framer Motion, Lenis, reduced-motion | Premium feel, no jank |
| 4 | 8 | SEO + performance: metadata, JSON-LD, image opt | LH 90+, CWV green |
| 5 | 9 | Pre-launch QA: cross-browser, a11y, soft launch | All tests pass |

# Phase 0 — Pre-flight (before any code)

Not in the original roadmap, but essential. These checks resolve open contradictions and lock decisions so the build doesn't stall mid-phase. Budget for one to two days.

BUNDLE-BUDGET RECONCILIATION

☐  Open Appendix B (dependency manifest) and Chapters 6.7 + 10.3 side by side [App. B, 6.7, 10.3]

☐  Confirm next-intl, @tanstack/react-query, next-pwa/Workbox and size-limit are in the manifest [App. B]

☐  Re-sum the 130KB First Load JS budget WITH the new libraries; confirm it still holds or document the new allocation [10.3]

☐  Re-check the 80KB animation budget against GSAP + ScrollTrigger + @gsap/react + Motion + Lenis [6.7]

☐  If a budget breaks: decide trade-off now (drop a lib, raise budget with sign-off, or defer a feature) and record the decision [15.1]

DECISIONS LOCKED

☐  Confirm brand name is final: “Aura Living” across repo, tokens, metadata, copy [1.2]

☐  Confirm single source of truth: design tokens in globals.css are never overridden in components [5, App. A]

☐  Confirm non-negotiables: App Router, RSC-by-default, COD-first checkout, WCAG 2.2 AA [1.4]

☐  Agree the first ADR records these locked decisions [28.3]

ACCOUNTS & ACCESS

☐  Vercel project created; GitHub repo connected [13.1]

☐  Domain registered; DNS plan noted (full config due Week 8) [15.3]

☐  WhatsApp Business number provisioned for the FAB [12.4]

☐  Placeholder content pipeline ready — same dimensions as real assets from day one [15.3]

EXIT CRITERION   Every dependency is accounted for against both budgets with no unresolved conflict; locked decisions are written into ADR-0001; Vercel + GitHub + domain access confirmed.

# Phase 1 — Foundation (Weeks 1–2)

Establish the technical foundation. The exit gate is concrete: staging loads with correct fonts and colours, all routes return placeholders without errors, CI runs green on every PR, and a preview deploy is generated per PR. Resist building pages here.

PROJECT SCAFFOLD

☐  Next.js 16 project scaffolded with TypeScript (strict mode) [3.1, 4]

☐  Tailwind CSS 4 configured; ESLint + Prettier + import-boundaries rules wired [4.4]

☐  Feature-based folder structure from Chapter 4 created (app/, features/, lib/, services/, hooks/, components/, types/, utils/) [4.1]

☐  Path aliases configured in tsconfig and resolving in ESLint/Vitest [4.3]

☐  File naming convention enforced: kebab-case files, PascalCase exports [4.2]

DESIGN SYSTEM FOUNDATION

☐  Design tokens implemented in globals.css and surfaced via tailwind.config.ts [5.1, App. A]

☐  Gold/black/cream colour tokens in place; contrast pairings verified [5.2, 11.4]

☐  Fluid type scale (Fraunces display + Inter body) wired via clamp() [5.3]

☐  Spacing, radius, elevation tokens added [5.4, 5.6]

☐  Z-index layering scale + breakpoint tokens added to globals.css [23.1, 23.2]

☐  Fonts loaded via next/font (Fraunces + Inter), zero-CLS, display:swap [5.3.2]

APP SHELL & ROUTING

☐  Root layout with html/body, fonts, and providers (Zustand, future analytics, future theme) [3.2]

☐  Route groups created: (marketing), (shop), (account), (editorial) [4.1]

☐  Placeholder pages for ALL 27 routes returning without errors [3.7, 29.5]

☐  loading.tsx / error.tsx / not-found.tsx skeletons at root [3.2]

☐  i18n framework (next-intl) bootstrapped with locale middleware (en + ur scaffold) [18.1, 18.2]

TOOLING, CI/CD & TEST HARNESS

☐  Vitest + React Testing Library configured; first unit test passing [16.1, 16.2]

☐  Playwright installed; MSW mock layer scaffolded (tests/mocks) [16.3]

☐  GitHub Actions pipeline: typecheck, lint, test, build, bundlesize, Lighthouse, axe [13.4, 16.6]

☐  Security headers + CSP set in next.config / middleware [17.1]

☐  Git branching + commit conventions + PR template adopted [28.1, 28.2]

☐  First deployment to staging (basic-auth protected); preview deploy generated per PR [13.3, 13.6]

EXIT CRITERION   Staging loads the homepage placeholder with correct fonts and colours; all 27 routes return placeholders without errors; CI runs green on every PR; a preview deployment is generated for every PR.

# Phase 2 — Core Pages (Weeks 3–5)

Build the full customer journey with placeholder data and NO animation beyond basic hover states. A working, plain purchase flow beats a beautiful broken one. Animations are explicitly out of scope here.

SHARED LAYOUT & DATA LAYER

☐  SiteHeader (transparent-to-solid on scroll), SiteFooter, MobileMenu, SearchOverlay [8.2]

☐  WhatsApp FAB present on every page (hidden on checkout) [12.4]

☐  TanStack Query provider + query-key conventions; services/ mock layer returning placeholder data [21.1, 21.2, 21.4]

☐  UI primitives built (Button, Input, Select, Badge, Card, Chip, Accordion, Dialog, Sheet, Skeleton, Toast, Textarea) [8.1]

HOMEPAGE

☐  All six below-the-fold sections built with placeholder imagery [7.1.2]

☐  Hero, CategoryTiles, FeaturedCollection, Bestsellers, EditorialBanner, Testimonials, NewsletterCTA [8.2]

☐  Trust-signal row rendered [12.5]

SHOP / PLP

☐  Product grid (4-col desktop / 2-col mobile) + ProductCard with quick-add [7.2.2]

☐  Filter & sort bar driving URL search params (shareable, crawlable) [7.2.1]

☐  Empty + loading (skeleton) states matching card dimensions [7.2.3, 24.1, 24.2]

PRODUCT DETAIL (PDP)

☐  Gallery (desktop thumb-strip / mobile swipe), info column, accordion tabs [7.3.1, 7.3.2]

☐  Related products + recently-viewed + read-only reviews [7.3.3]

☐  Trust badges + WhatsApp enquiry button [7.3.2, 12.5]

CART, CHECKOUT & CONFIRMATION

☐  Cart drawer (auto-opens on add) + full cart page + delightful empty state [7.4]

☐  Zustand cart store with persist + skipHydration [3.5]

☐  Single-page checkout: Contact, Shipping, Delivery, Payment sections [7.5.1]

☐  COD selected by default and listed first; reassuring (not cautionary) copy [12.1]

☐  Gift options section: wrap, handwritten note, ship-to-different-address [20.1, 20.2]

☐  Payment selector (COD, JazzCash, Easypaisa, Card, Bank) with per-method fields [12.2]

☐  Order summary (sticky) with totals + coupon input [7.5.2, 22.2]

☐  React Hook Form + Zod validation, onBlur fields / onSubmit sections [3.6]

☐  Order confirmation page with summary + analytics purchase event hook [7.20]

ACCOUNT & SUPPORTING PAGES

☐  Auth pages (login/register), account dashboard, orders, addresses, wishlist, settings [7.6, 7.7]

☐  Search results page + client-side index (frontend phase) [7.10, 26.1]

☐  Marketing/legal pages: about, contact, faq, shipping-returns, privacy, terms, lookbook, journal [7.11–7.18]

☐  404, accessibility-statement, and maintenance/503 pages [7.19, 27.4, 29.2]

CROSS-CUTTING

☐  All pages responsive: mobile / tablet / desktop [12.3]

☐  Component tests with MSW for core components [16.2, 16.3]

☐  Consolidated empty/loading/error states applied [24.1, 24.2, 24.3]

EXIT CRITERION   A user can complete the full journey from homepage to order confirmation on placeholder data; all pages are responsive; all forms validate correctly; Lighthouse performance is above 70 on the homepage and PDP. (No animations beyond hover.)

# Phase 3 — Polish & Animations (Weeks 6–7)

Add the GSAP / Framer Motion / Lenis signature motion. This is where the bundle budget bites — Phase 0's reconciliation pays off here. Every animation must respect prefers-reduced-motion.

MOTION INFRASTRUCTURE

☐  Lenis smooth-scroll provider (desktop only; native scroll on touch) [6.4]

☐  Reusable Parallax wrapper (GSAP ScrollTrigger, GPU-only, reduced-motion-aware) [6.2, 6.5]

☐  Reusable Reveal wrapper (Framer Motion whileInView) [6.3]

☐  MagneticButton wrapper (useMotionValue + useSpring), used sparingly on primary CTAs [6.3]

☐  useReducedMotion as single source of truth; verify GSAP wiring [6.6]

PAGE-LEVEL MOTION

☐  Homepage hero entrance (~1200ms, runs once on mount) [7.1.3]

☐  Homepage section reveals with 80ms staggers [7.1.3]

☐  Pinned featured-collection section (desktop ≥ 1024px; static carousel fallback on mobile) [7.1.2]

☐  PDP gallery transitions [7.3.1]

☐  Cart drawer + mobile menu enter/exit via AnimatePresence [6.3]

☐  Testimonial marquee (desktop) / swipe (mobile) [7.1.2]

☐  404 + order-confirmation illustrations and path-draw animations [7.19, 7.20]

☐  View Transitions API page transitions, reduced-motion aware [29.1]

GUARDRAILS

☐  Reduced-motion fallbacks designed as intentional static end-states for ALL of the above [6.6]

☐  No forbidden patterns: no layout-property animation, no setTimeout/setInterval anim, max 3 concurrent [6.7]

☐  Animation JS budget (80KB gz) re-verified in CI after additions [6.7]

EXIT CRITERION   The site feels premium and choreographed on desktop; all animations respect prefers-reduced-motion; no animation causes visible jank on a mid-range mobile device (Moto G4 class); Lighthouse performance has NOT regressed from Phase 2.

# Phase 4 — SEO & Performance (Week 8)

Optimisation phase. Implement the SEO layer and tune performance to hit the Core Web Vitals targets in Chapter 10.

SEO IMPLEMENTATION

☐  Metadata API (generateMetadata / static metadata) on every page [9.1.1]

☐  JSON-LD: Product, BreadcrumbList, Organization, FAQPage, Article, WebSite [9.3]

☐  Dynamic sitemap (app/sitemap.ts) covering products, collections, journal, lookbook, static [9.4]

☐  robots.ts with staging-vs-production rules [9.4]

☐  Open Graph + Twitter Card tags; default OG image in place [9.5]

☐  Filtered/paginated PLP canonicalization + locale duplicate-content handling [27.1, 27.3]

☐  Image sitemap + image SEO pass [27.2]

☐  hreflang wired for en/ur locales [18.4]

PERFORMANCE TUNING

☐  Image optimisation pass: correct sizes, AVIF/WebP, lazy loading, explicit width/height [10.2]

☐  Hero images preloaded with fetchpriority=high [10.2]

☐  Bundle size audit; dynamic-import oversized routes (GSAP/parallax desktop-only) [10.3]

☐  Font loading verified (zero render-block, zero CLS) [10.4]

☐  Caching tiers confirmed: browser immutable, edge, ISR 300s [10.5]

☐  PWA: manifest + Workbox service worker + offline fallback shipped [19.1, 19.2, 19.3]

☐  Mobile budget: ≤ 800KB page weight; tested on simulated Pakistani 4G [10.6]

☐  Privacy: cookie-consent UI + analytics event taxonomy + funnels wired [25.1, 25.2, 25.3]

EXIT CRITERION   Lighthouse performance 90+ on all primary pages; all Core Web Vitals in the green; all structured data valid via the Rich Results Test; sitemap submitted to Google Search Console.

# Phase 5 — Pre-Launch QA (Week 9)

Final quality assurance, then a soft launch (no marketing, monitoring for issues) before the official marketing launch in Week 10.

COMPATIBILITY

☐  Cross-browser: Chrome, Safari, Firefox, Edge, Samsung Internet, iOS Safari [14.5]

☐  Cross-device: iPhone SE, iPhone 14, Galaxy S22, iPad, MacBook, low-end Android [14.5]

ACCESSIBILITY (WCAG 2.2 AA)

☐  axe-core scan: zero violations across E2E pages [11, 16.6]

☐  Manual keyboard-only pass: focus visible, no traps, logical order [11.2]

☐  Screen-reader pass: NVDA (Windows) + VoiceOver (macOS/iOS) on home, PDP, cart, checkout [11.3]

☐  Focus management on route change, filter change, add-to-cart, form errors [11.5]

SECURITY & RESILIENCE

☐  COD/OTP abuse prevention + velocity checks verified [17.3, 17.4]

☐  Dependency audit / supply-chain check clean [17.5]

☐  Critical E2E journeys green (COD happy path, JazzCash redirect, cart persistence, search/filter, wishlist) [16.4]

CONTENT, LEGAL & LAUNCH

☐  Content review: all copy, images, links [14.5]

☐  Legal review: privacy policy + terms of service [14.5]

☐  Performance testing on simulated 4G recorded [14.5, 10.6]

☐  Domain / DNS / SSL verified [15.3]

☐  Production deployment runbook written [14.5]

☐  Back-in-stock + inventory handling verified [29.3]

☐  Service-interface TypeScript contracts ready for the full-stack (Supabase) phase [29.4]

☐  Soft launch to production at end of Week 9; monitoring in place [14.5]

EXIT CRITERION   All compatibility, accessibility, security, and content checks pass; the production runbook is complete; the site is soft-launched and monitored, ready for the Week 10 marketing launch.

# Standing principles (every phase)

These hold across all phases. The failure mode for a plan this thorough is not missing information — it is erosion under time pressure. Guard these.

☐  Design tokens are the single source of truth — no inline styles, no magic numbers [5]

☐  Server Components by default; Client Components only at interactive leaves [3.3]

☐  Build tests and accessibility WITH each feature, never as a cleanup pass [11, 16]

☐  Every animation respects prefers-reduced-motion [6.6]

☐  Keep the v1.1 plan as source of truth; reject changes that contradict locked Ch. 1–15 decisions [1.4]

☐  New architectural choices get an ADR; roadmap stays frozen — new features deferred to v2 [28.3, 15.3]

☐  Bundle + animation budgets re-checked in CI on every PR [6.7, 10.3]

Source: Aura Living Frontend Architecture Plan v1.1. Bracketed references point to chapters in that document. This checklist is a build aid, not a substitute for the full specification.